## Slide 1: Event Planning 101
USU Reservation Center
559.278.6024

## Slide 2: 3+ Months Prior to your Event
Identify your event’s goals Brainstorm project ideas Choose your event date and time.
Check Fresno State’s Events Calendar
Check OrgSync’s Master Calendar
Review your event budget
Reach out to other Fresno State organizations to assess co-programming potential
Reach out to potential vendors
Delegate immediate and long-term responsibilities
Submit space reservation request(s)
Submit Alcohol Request (if applicable)

## Slide 3: 6-8 Weeks Prior to your Event
Finalize budget
Register your event on OrgSync
Submit vendor documentation (if applicable)
Contract (if applicable)
Certificate of Insurance (if applicable)

## Slide 4: 3-6 Weeks Prior to your Event
Communicate with Technical Supervisor (if applicable)
Submit A/V Request Form to Technical Supervisor
Submit Catering Request (if applicable)
Submit Food Waiver Request (if applicable)
Submit Parking Request/Notification (if applicable)

## Slide 5: 1-3 Weeks Prior to your Event
Confirm orders with campus support services and communicate any changes
Confirm orders with vendors and communicate any changes
Consult the Reservation Center if you’re awaiting contract approval
Purchase decorations and/or supplies
Get promotional materials approved from the Reservation Center
Distribute promotional materials
Create event on social media and send initial invites

## Slide 6: Week of the Event
Confirm headcount with caterer (if applicable)
Get the word out by tabling
Continue to advertise on social media
Review delegated responsibilities

## Slide 7: Day of the Event
Arrive on time for setup
Have a blast!
Clean up afterwards
Return all material to respective places

## Slide 8: Week After the Event- Evaluation
Reflect on event- Did it meet your expectations
What could have been done differently
Discuss strengths and weaknesses with organization
Begin planning your next event!

## Slide 9: Off Campus Events
Student organizations choosing to sponsor off campus events accept responsibility for the event. Each recognized student organization is expected to conduct their activities in accordance with relevant law, the Fresno State Student Code of Conduct, the Fresno State Student Organization Code of Conduct, CSU and Fresno State policy (which are all applicable to both on-campus and off-campus events).
Officers of the organization are responsible for informing members of the organization of the above expectations and requirements.